## sprint 1
Project | Story | Task | Start | Day 3 | Day 2 | Day 1
sejarah dan definisi musik | Story 1 | Task 1 | 5 | 1 | 2 | 2
jenis musik | Story 2 | Task 2.1 | 2 | 2 | 1 | 0
musik klasik | Story 2 | Task 2.2 | 3 | 2 | 3 | 0
musik seni | Story 2 | Task 2.3 | 2 | 2 | 1 | 0
musik reggae | Story 2 | Task 2.4 | 3 | 2 | 0 | 0
musik pop | Story 2 | Task 2.5 | 3 | 3 | 0 | 0
musik RnB | Story 2 | Task 2.6 | 3 | 3 | 0 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 21 | 18.9 | 16.8 | 14.7
Actual - Remaining efforts in uninterrupted working hours |  |  | 21 | 15 | 7 | 2

## sprint 2
Project | Story | Task | Start | Day 3 | Day 2 | Day 1
musik jazz | Story 1 | Task 1 | 5 | 1 | 2 | 2
musik gospel | Story 2 | Task 2 | 4 | 1 | 1 | 2
musik blues | Story 3 | Task 3 | 6 | 1 | 2 | 3
musik rock | Story 4 | Task 4 | 5 | 2 | 1 | 2
musik amerika latin | Story 4 | Task 5 | 4 | 2 | 1 | 1
Ideal - Remaining efforts in uninterrupted working hours |  |  | 24 | 21.6 | 19.2 | 16.8
Actual - Remaining efforts in uninterrupted working hours |  |  | 24 | 7 | 7 | 10

## sprint 3
Project | Story | Task | Start | Day 3 | Day 2 | Day 1
jenis suara | Story 1 | Task 1 | 5 | 1 | 2 | 2
terapi musik | Story 2 | Task 2 | 4 | 1 | 1 | 2
musik country | Story 3 | Task 3 | 6 | 1 | 2 | 3
tokoh musik | Story 4 | Task 4 | 5 | 2 | 1 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 20 | 18 | 16 | 14
Actual - Remaining efforts in uninterrupted working hours |  |  | 20 | 5 | 6 | 9

## sprint 4
Project | Story | Task | Start | Day 3 | Day 2 | Day 1
gitar | Story 1 | Task 1 | 5 | 1 | 2 | 2
biola | Story 2 | Task 2 | 4 | 1 | 1 | 2
piano | Story 3 | Task 3 | 6 | 1 | 2 | 3
drum | Story 4 | Task 4 | 5 | 2 | 1 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 20 | 18 | 16 | 14
Actual - Remaining efforts in uninterrupted working hours |  |  | 20 | 5 | 6 | 9